MediLocker

Implementation Plan — Completion of Outstanding Scope
Six-phase plan covering the remaining 40% of the specified system, from defect repair to secure deployment

| Document Property | Detail |
| --- | --- |
| Project | MediLocker — Secure Cloud-Based Digital Medical Record Management Platform |
| Document | Implementation Plan — Completion of Outstanding Scope |
| Version & Status | Version 2.0 — Draft for approval |
| Date | 13 September 2026 |
| Scope | Remaining work only (~40%); delivered scope is not restated |
| Phases | 6 phases, 58 tasks |
| Critical Path | Phase 1 → 2 → 3 → 5 (4–6 weeks, single developer) |
| Companion Documents | DATABASE_SCHEMA_AND_ARCHITECTURE.md, ROLE_AND_PAGE_WISE_FEATURE_MAP.md |

Project: MediLocker — Secure Cloud-Based Digital Medical Record Management Platform

Document: Implementation Plan — Completion of Outstanding Scope

Version: 3.0

Date: 13 September 2026

Status: All six phases delivered

Companion documents: DATABASE_SCHEMA_AND_ARCHITECTURE.md, ROLE_AND_PAGE_WISE_FEATURE_MAP.md

## 0. Delivery Status

| Phase | Status | Evidence |
| --- | --- | --- |
| 1 — Foundation and defect repair | Complete | Backend and frontend typecheck clean; npm run build succeeds in both |
| 2 — Hardening and audit integrity | Complete | Audit chain verifies intact through GET /api/v1/admin/audit-logs/verify-chain |
| 3 — Encrypted file pipeline | Complete | Files are AES-256-GCM encrypted before storage; stored objects are not the original bytes; a tampered object fails to decrypt |
| 4 — Cryptographic identity | Complete | Real TOTP with backup codes, session-bound tokens with immediate revocation, ECDSA P-256 prescription signing verified server-side |
| 5 — Platform services | Complete | Consent cache with instant revocation, five scheduled jobs, notification outbox, append-only hash-chained ledger with a database immutability trigger |
| 6 — Frontend and delivery | Complete | Shared layout with navigation and sign-out, single API client, TanStack Query, error boundary, Docker compose, GitHub Actions |

77 integration tests pass; `npm run smoke` reports 78/78 routes below 500.

Migrations: V1 initial schema, V2 file pipeline and crypto identity (user_sessions, mfa_backup_codes, storage provenance), V3 ledger and delivery (ledger_entries, delivery bookkeeping, integrity-sweep columns). The database holds 20 tables.

### 0.1 Measured, not asserted

The system-health endpoint reports real values. Against the current development database (a remote Supabase instance) the numbers are:

| Metric | Measured | Target | Note |
| --- | --- | --- | --- |
| Database round trip | ~1300 ms | — | Remote region; dominates every uncached path |
| Consent evaluation, cache hit | <1 ms | <10 ms (NFR06) | Meets the target |
| Consent evaluation, mixed | ~90 ms | <10 ms (NFR06) | Does not meet the target on a cold cache against a remote database |
| Ledger | INTACT | — | Verified over all entries |
| Cache | MEMORY | REDIS | In-process; not shared between instances until REDIS_URL is set |

The mixed figure is the honest one to quote: NFR06 is met on the cached path and missed on the uncached path with this database placement. A co-located database and a Redis instance would both be needed to meet it generally.

Commands to reproduce the evidence:

cd backend && npm run typecheck && npm test

cd frontend && npm run build

cd backend && npm run dev

cd backend && npm run smoke

Defects found during execution that were not in the original register are recorded as D13–D22 in Appendix A.

## 1. Scope of This Plan

This plan covers only the work that remains — approximately 40% of the specified system. The database schema, the API surface, all 31 screens, consent evaluation, the break-glass state machine, admin verification workflows and HMS key management are already built and are not restated here.

What remains falls into six deliverables:

| # | Outstanding deliverable | Why it is required |
| --- | --- | --- |
| 1 | Defect repair and a compiling build | Seven schema mismatches throw at runtime; the frontend production build fails; the JWT secret falls back to a committed literal |
| 2 | Backend hardening and audit integrity | No validation, no error handling, no rate limiting, no account lockout; the audit hash chain is never written |
| 3 | Encrypted file pipeline | No file is ever transmitted or stored. This is the platform's core function and the largest single gap |
| 4 | Cryptographic identity | MFA codes and prescription signatures are placeholder strings; public verification ignores its input |
| 5 | Platform services and automation | No consent cache, no scheduled expiry, no notification delivery, no integrity sweep, no real ledger |
| 6 | Frontend completion and delivery | No navigation, no logout, no shared layout, no API client, no containers, no CI |

Each becomes a phase below. All six are required to complete the project as specified; none can be dropped without reducing scope.

### 1.1 Deferred beyond this plan

| Item | Rationale | Revisit when |
| --- | --- | --- |
| Hyperledger Fabric network | Weeks of infrastructure work. Task P5-08 delivers the same tamper-evidence property with an append-only PostgreSQL ledger | A partner institution requires a shared permissioned ledger |
| Apache Kafka event bus | The scheduler plus the notifications table functions as an adequate outbox at current scale | Multi-service fan-out becomes a genuine requirement |
| Microservice decomposition | The monolith is not yet a bottleneck | Independent scaling or separate team ownership is needed |
| UIDAI / ABDM production integration | Requires external accreditation and a sandbox agreement | Accreditation is obtained |
| PostgreSQL Row-Level Security | Valuable defence in depth, but the application-layer checks in Phase 2 must be correct first | Phase 2 closes |

### 1.2 Basis of assessment

Defects in Appendix A were identified by reading application code against backend/prisma/schema.prisma. Dependencies were not installed at review time, so nothing was compiled or executed. Each defect should be confirmed once Phase 1 makes the project runnable; Phase 1 includes a smoke script specifically to expose any that were missed.

## 2. Guiding Principles

Correctness before capability. No new feature work begins until the project compiles and every existing endpoint returns a non-5xx response.

Interfaces before vendors. Encryption, object storage and ledger anchoring are each introduced behind an interface with a local implementation first. Cloud providers are substituted later without changing call sites.

Never trust the client for security-critical values. Document hashes, digital signatures and consent decisions are computed or verified on the server.

Honest user interface. No screen may assert a security property the system does not implement. Until the relevant phase lands, such claims are removed or explicitly labelled as prototype behaviour.

Every change is provable. Each phase carries acceptance criteria that can be demonstrated, not merely asserted.

## 3. Phase 1 — Foundation and Defect Repair

Effort: 2 days Depends on: — Blocks: every other phase

### 3.1 Environment

| ID | Task | Deliverable |
| --- | --- | --- |
| P1-01 | Run npm run install:all; commit both lockfiles | Reproducible dependency tree |
| P1-02 | Generate a 32-byte JWT_SECRET into backend/.env; abort startup if absent rather than falling back to the committed development string | backend/src/config/env.ts with fail-fast validation |
| P1-03 | Apply V1__init_medilocker_schema.sql; run npx prisma generate; confirm with prisma db pull that no drift exists | Migrated database, generated client, drift report |
| P1-04 | Add seed, typecheck, build and start scripts to backend/package.json; execute the seed | Populated development dataset |
| P1-05 | Move get_patient.js, get_users.js, test-db.js, test_registration.js and scratch_*.js out of the backend root into backend/scripts/, or delete them | Clean package root |
| P1-06 | Add backend/.env.example, maintained from here onward | Documented configuration surface |

### 3.2 Defect repair

| ID | Task | Detail |
| --- | --- | --- |
| P1-07 | Fix defect D1 | Generate consent_token_hash on consent creation — sha256(patient_id + doctor_id + valid_until + random nonce). Without it, every consent grant fails on a not-null unique column |
| P1-08 | Fix defects D2 and D6 | Remove the non-existent consent_audit_logs include; read vault_number through the patient_vaults relation rather than patients |
| P1-09 | Fix defects D3, D4 and D5 | Correct file_type to file_mime_type; remove the description search filter or add the column; add include: { patients: true } to the vault lookup so the notification receives a valid user_id |
| P1-10 | Fix defect D7 | Skip the break_glass_record_accesses insert when the patient has no records, instead of writing a dummy UUID that violates the foreign key |
| P1-11 | Fix defect D8 | Add "types": ["node"] to backend/tsconfig.json; resolve errors until tsc --noEmit is clean |
| P1-12 | Fix defect D9 | Add "jsx": "react-jsx" to frontend/tsconfig.json; replace the bare JSX.Element in App.tsx:37 with React.JSX.Element; clear the unused-import errors noUnusedLocals will surface across the page components |
| P1-13 | Fix defect D10 | Remove the duplicated legacy /api/* route mounts; the frontend uses /api/v1 exclusively |
| P1-14 | Author an endpoint smoke script exercising all ~60 routes against seeded data | backend/scripts/smoke.ts |

Acceptance criteria

npm run dev at the repository root starts both servers.

A seeded patient completes login and multi-factor entry and reaches a dashboard rendering seeded records.

tsc --noEmit is clean in both packages; npm run build succeeds in frontend/.

The smoke script reports zero 5xx responses across all routes.

## 4. Phase 2 — Backend Hardening and Audit Integrity

Effort: 3–5 days Depends on: Phase 1 Blocks: Phases 3 and 4

| ID | Task | Detail |
| --- | --- | --- |
| P2-01 | Introduce zod schemas and a single validate(schema) middleware for every body, query and parameter; reject unknown fields |  |
| P2-02 | Add an asyncHandler wrapper and a central error handler; stop returning raw error.message to clients in production |  |
| P2-03 | Add helmet; restrict CORS to the configured frontend origin, replacing the unrestricted app.use(cors()) |  |
| P2-04 | Add express-rate-limit, applied strictly to /auth/login, /auth/verify-mfa and all /public/* routes |  |
| P2-05 | Implement account lockout in login using the existing but unused failed_login_attempts and lockout_until columns |  |
| P2-06 | Implement audit middleware recording every state-changing request and every record read or decrypt, with genuine previous_log_hash chaining. Serialise writes through a transaction or advisory lock so the chain stays linear under concurrency |  |
| P2-07 | Add GET /admin/audit-logs/verify-chain, walking the chain and reporting the first break |  |
| P2-08 | Audit every handler for resource ownership. vault/records/:id/blockchain-proof and emergency/terminate currently act without confirming the caller owns or is party to the resource |  |
| P2-09 | Add integration tests (Vitest with supertest against a test database) covering authentication, the consent grant → use → revoke cycle, and break-glass approve → read → expire |  |

Acceptance criteria

Malformed payloads return 400 with field-level messages, never 500.

Eleven consecutive failed logins lock an account for the configured interval.

The chain-verification endpoint reports an intact chain after a seeded run, and correctly identifies the position of a deliberately tampered row.

The integration suite passes.

## 5. Phase 3 — Encrypted File Pipeline

Effort: 4–6 days Depends on: Phase 2 May run parallel to: Phases 4 and 6

The highest-value remaining deliverable. It converts a demonstration into a working product.

| ID | Task | Detail |
| --- | --- | --- |
| P3-01 | Add multer with memory storage, a MIME allowlist (PDF, PNG, JPEG, DICOM) and a size ceiling |  |
| P3-02 | Implement backend/src/services/crypto.ts: generate a per-file data encryption key, encrypt with AES-256-GCM, persist encrypted_dek, iv_bytes and the authentication tag |  |
| P3-03 | Define a KeyProvider interface. Ship LocalKeyProvider (master key from environment) first; KmsKeyProvider follows in Phase 5 without altering call sites |  |
| P3-04 | Define an ObjectStorage interface. Ship LocalDiskStorage first; S3Storage targeting ap-south-1 follows |  |
| P3-05 | Compute SHA-256 server-side over the received buffer. The client-supplied hash is discarded, not stored |  |
| P3-06 | Implement GET /vault/records/:id/download returning a short-lived presigned URL or a streamed decryption, gated on consent and recorded in the audit log |  |
| P3-07 | Replace frontend simulations: real crypto.subtle.digest in DoctorUpload, real retrieval and rendering in PatientVault (currently a two-second timer), real file hashing in VerifyDocument |  |
| P3-08 | Backfill or clearly quarantine the mock-keyed records created by the seed and by earlier testing |  |

Acceptance criteria

A doctor uploads a PDF; the stored object is unreadable without the key.

The owning patient retrieves and views it.

A doctor without consent is refused; a doctor whose consent blocks that category is refused.

All four events appear in the audit log with correct actor and resource identifiers.

## 6. Phase 4 — Cryptographic Identity

Effort: 4–6 days Depends on: Phase 2 May run parallel to: Phases 3 and 6

| ID | Task | Detail |
| --- | --- | --- |
| P4-01 | Implement TOTP with otplib. On registration generate a secret, store it encrypted in users.mfa_secret, and return an otpauth:// URI rendered as a QR code client-side |  |
| P4-02 | Replace the hardcoded 123456 comparison in verify-mfa with real time-window verification; add single-use backup codes |  |
| P4-03 | Replace the hardcoded emergency approval code in emergencyController.approveRequest with a generated, hashed, time-limited code delivered to the approving administrator |  |
| P4-04 | Generate the doctor keypair in the browser using crypto.subtle (ECDSA P-256), retaining the non-extractable private key in IndexedDB; transmit only the public key PEM and its true fingerprint |  |
| P4-05 | Sign the canonical prescription JSON client-side; verify server-side against doctors.public_key_pem before insertion, setting is_signature_valid from the actual result rather than the current unconditional true |  |
| P4-06 | Rewrite public/verify-prescription to accept a prescription identifier or QR payload, re-canonicalise the document and verify the stored signature — removing the behaviour that returns the first table row irrespective of input |  |
| P4-07 | Generate the signed prescription PDF with an embedded QR code addressing /verify |  |
| P4-08 | Implement password change and active device session listing with remote logout (Screen 3.7), for which no endpoint or interface currently exists |  |

Acceptance criteria

An authenticator application produces codes the server accepts, and rejects codes outside the valid window.

A prescription with a single altered dosage field fails public verification; the original passes.

The public verifier page reflects both outcomes accurately.

A patient can change their password and terminate other sessions.

## 7. Phase 5 — Platform Services and Automation

Effort: 5–7 days Depends on: Phases 3 and 4

| ID | Task | Detail |
| --- | --- | --- |
| P5-01 | Add Redis. Cache consent decisions at consent:{patient_id}:{doctor_id} with a TTL matching valid_until; delete the key on revocation |  |
| P5-02 | Instrument consent evaluation with cache-hit ratio and latency metrics, so the sub-10ms requirement is measured rather than asserted |  |
| P5-03 | Introduce a job scheduler (BullMQ on the same Redis instance; node-cron is acceptable as a simpler start) |  |
| P5-04 | Scheduled job: expire break-glass sessions at session_expires_at. Expiry is currently evaluated only when a session is read |  |
| P5-05 | Scheduled job: expire consents at valid_until and emit reminder notifications 24 hours beforehand |  |
| P5-06 | Scheduled job: integrity sweep re-hashing stored objects, comparing against blockchain_anchors, raising an alert on mismatch |  |
| P5-07 | Notification delivery worker draining notifications rows with delivery_status = 'PENDING' via email and SMS providers, updating delivered_at |  |
| P5-08 | Implement services/ledger.ts behind an interface, backed by an append-only PostgreSQL table with hash chaining, replacing the mock_tx_${Date.now()} placeholder |  |
| P5-09 | Derive the emergency clinical snapshot from ALLERGY_RECORD and CHRONIC_DISEASE_HISTORY records plus current prescriptions, replacing the hardcoded allergy and condition arrays |  |
| P5-10 | Replace Math.random() in the administrator system-health endpoint with real process, database and Redis metrics; remove the fabricated Kafka panel or label it as not yet deployed |  |
| P5-11 | Substitute KmsKeyProvider and S3Storage for the local implementations from Phase 3 |  |

Acceptance criteria

A revoked consent is refused within one second, demonstrated by a timed test.

A break-glass session becomes unusable at expiry without any read having occurred.

Modifying a stored file causes the integrity sweep to raise an alert.

A notification row transitions to delivered with a provider receipt.

No figure on the system-health screen is fabricated.

## 8. Phase 6 — Frontend Completion and Delivery

Effort: 4–6 days Depends on: Phase 1 May run parallel to: Phases 2 through 5

| ID | Task | Detail |
| --- | --- | --- |
| P6-01 | Build a shared AppLayout with a role-aware sidebar, header, logout control and session-expiry handling. No navigation or logout affordance exists anywhere in the application today |  |
| P6-02 | Create src/lib/api.ts: base URL from VITE_API_URL, authorisation header injected once, 401 triggering logout and redirect, typed responses. This replaces roughly sixty hand-written fetch calls each re-pasting the bearer token |  |
| P6-03 | Adopt TanStack Query for caching, loading and error states, as already claimed in README.md |  |
| P6-04 | Add error boundaries, loading skeletons, empty states and toast notifications |  |
| P6-05 | Accessibility pass: form labels, focus management on modals, keyboard navigation, colour contrast |  |
| P6-06 | Add a Dockerfile per package and a docker-compose.yml covering PostgreSQL, Redis, backend and frontend |  |
| P6-07 | Reconcile documentation with the implementation: record the Express monolith as the current architecture, retaining the eight-microservice topology as a target state; repair the file:///d:/MediLocker/... absolute links in README.md, which resolve for no one |  |
| P6-08 | GitHub Actions pipeline: typecheck → lint → test → build on every pull request |  |

Acceptance criteria

Every authenticated page renders within the shared layout with a working logout control.

No component constructs an authorisation header directly.

docker compose up brings the full stack to a healthy state from a clean checkout.

The pipeline passes on a pull request.

## 9. Schedule and Sequencing

| Phase | Effort | Depends on | May run parallel with |
| --- | --- | --- | --- |
| 1 — Foundation and defect repair | 2 days | — | — |
| 2 — Hardening and audit integrity | 3–5 days | 1 | 6 |
| 3 — Encrypted file pipeline | 4–6 days | 2 | 4, 6 |
| 4 — Cryptographic identity | 4–6 days | 2 | 3, 6 |
| 5 — Platform services | 5–7 days | 3, 4 | 6 |
| 6 — Frontend and delivery | 4–6 days | 1 | 2, 3, 4, 5 |

Critical path: 1 → 2 → 3 → 5. Phase 4 runs alongside Phase 3; Phase 6 runs alongside everything from the close of Phase 1.

| Resourcing | Duration |
| --- | --- |
| One developer | 4–6 weeks |
| Two developers | 3–4 weeks — the second takes Phase 6 from the close of Phase 1, then Phase 4 from the close of Phase 2 |

Recommended first commit: Phase 1 in full. It is two days of work, it converts a codebase that currently cannot build into one that runs end to end, and all five remaining phases are blocked behind it.

## 10. Quality Gates

A task is complete only when all of the following hold.

tsc --noEmit is clean in both packages.

npm run build succeeds in both packages.

New or changed behaviour is covered by a test.

Security-relevant changes are accompanied by a negative test proving the denial path.

No endpoint returns a raw exception message to a client.

No user-facing string asserts a security property the code does not implement.

## 11. Configuration to Be Added

| Variable | Package | Purpose | Phase |
| --- | --- | --- | --- |
| JWT_SECRET | backend | Token signing — currently missing, falls back to a committed literal | 1 |
| PORT, NODE_ENV, CORS_ORIGIN | backend | Server and origin configuration | 2 |
| KMS_MASTER_KEY | backend | Local key provider master key | 3 |
| STORAGE_DRIVER, STORAGE_PATH | backend | Object storage selection | 3 |
| REDIS_URL | backend | Consent cache and job queue | 5 |
| AWS_REGION, AWS_KMS_KEY_ID, S3_BUCKET | backend | Cloud providers | 5 |
| SMTP_*, SMS_* | backend | Notification delivery | 5 |
| VITE_API_URL | frontend | API base URL | 6 |

DATABASE_URL and DIRECT_URL are already present. No secret is committed.

## 12. Testing Strategy

| Level | Tooling | Introduced | Coverage target |
| --- | --- | --- | --- |
| Endpoint smoke | Custom script | Phase 1 | All ~60 routes return non-5xx |
| Integration | Vitest, supertest, test database | Phase 2 | Authentication, consent lifecycle, break-glass lifecycle |
| Unit | Vitest | Phase 3 | Encryption, hashing, signature verification |
| Security regression | Vitest | Phases 2–4 | Every denial path: absent consent, blocked category, expired session, invalid signature, forged token |
| Frontend component | Vitest, Testing Library | Phase 6 | Layout, API client, protected routing |
| End to end | Playwright (optional) | Phase 6 | Patient and doctor primary journeys |

Security regression tests are mandatory, not optional. For a health-records platform the denial paths matter more than the success paths.

## 13. Risks and Mitigations

| ID | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| R1 | The interface presents "AES-256 Encrypted · Zero-Trust Access · Blockchain Anchored" over a timer and Math.random(). Demonstrating this to a clinical or regulatory audience as working would be a material misrepresentation | Severe | Deliver Phases 3 to 5, or label the build a prototype in the interface until they land. Principle 4 in §2 |
| R2 | Real patient data entering the system before encryption, audit chaining and Row-Level Security are genuine | Severe — DPDP Act 2023 exposure | Synthetic data only until Phase 5 completes. Gate production access on a security review |
| R3 | Unrestricted CORS combined with the fallback JWT secret means anyone holding the repository can forge a platform-administrator token | Severe | Tasks P1-02 and P2-03. Not deferrable |
| R4 | Defects in Appendix A were found by reading, not by running; more may surface once the project executes | Moderate | Task P1-14 exists to expose the remainder before Phase 2 begins |
| R5 | The Phase 3 client-side decryption model requires the browser to hold key material; a naive implementation leaks keys to the page | Significant | Use non-extractable crypto.subtle keys; prefer server-side decryption with short-lived presigned URLs where the threat model permits |
| R6 | Phases 3 and 4 both touch prescription creation and may conflict if run in parallel | Moderate | Phase 3 owns the record and storage layer; Phase 4 owns signing. Agree the prescriptions contract before both start |

## Appendix A — Defect Register

| ID | Location | Defect | Severity | Task |
| --- | --- | --- | --- | --- |
| D1 | consentController.ts:38 | consents.create omits the required unique consent_token_hash; every consent grant fails | Blocker | P1-07 |
| D2 | consentController.ts:110 | Includes a consent_audit_logs relation absent from the schema; consent history always returns 500 | Blocker | P1-08 |
| D3 | vaultController.ts:78 | Reads record.file_type; the schema field is file_mime_type | High | P1-09 |
| D4 | vaultController.ts:26 | Filters on a description column that medical_records does not have | High | P1-09 |
| D5 | vaultController.ts:141 | vault.patients?.user_id resolves to an empty string because the query has no include; the notification insert violates its foreign key | High | P1-09 |
| D6 | adminController.ts:227 | Selects vault_number from patients; it belongs to patient_vaults. /admin/disputes always returns 500 | Blocker | P1-08 |
| D7 | emergencyController.ts:175 | Inserts a dummy zero UUID into break_glass_record_accesses when the patient has no records, violating the foreign key | High | P1-10 |
| D8 | backend/tsconfig.json | "types": [] with no @types/node, while the code uses process.env and imports crypto. Runs under tsx, which does not typecheck, but will not compile | High | P1-11 |
| D9 | frontend/tsconfig.json, App.tsx:37 | No "jsx" compiler option, so npm run build fails on every .tsx; the bare JSX.Element namespace is no longer global in React 19 types | Blocker | P1-12 |
| D10 | backend/src/index.ts | Every route is mounted twice, at /api/v1/* and legacy /api/*; only /api/v1 is used | Low | P1-13 |
| D11 | backend/.env | JWT_SECRET absent; the application falls back to the committed literal 'fallback-secret-key-for-dev' | Critical | P1-02 |
| D12 | backend/ root | Scratch scripts committed at the package root | Low | P1-05 |
| D13 | frontend/package.json | react and react-dom were never declared as dependencies, and @types/react / @types/react-dom were absent entirely. Accounted for roughly 4,000 of the 4,045 initial frontend type errors | Blocker | Fixed in Phase 1 |
| D14 | Any endpoint returning medical_records, patient_vaults or blockchain_anchors | BigInt columns are not valid JSON, so res.json threw *Do not know how to serialize a BigInt*. Latent until a row actually existed — six endpoints returned 500 once data was present | Blocker | Fixed in Phase 1 (global JSON replacer) |
| D15 | backend/src/middlewares/authMiddleware.ts | The short-lived token issued between password entry and MFA was accepted as a session token. Any route without a role guard — notably /api/v1/notifications — was reachable with only a password, bypassing the second factor | Critical | Fixed in Phase 1 |
| D16 | backend/src/seed.ts | Cleanup deleted parents before children and could only ever run once; the audit-immutability trigger then blocked the SetNull cascade from users, so re-seeding failed outright | High | Fixed in Phase 1 |
| D17 | backend/src/controllers/emergencyController.ts | getSessionData and terminateSession performed no ownership check: any doctor could read another physician's break-glass payload, and any hospital admin could terminate any session | Critical | Fixed in Phase 2 (P2-08) |
| D18 | backend/src/services/auditLog.ts | Hashing JSON.stringify(details) is unstable across a jsonb round trip because Postgres does not preserve key order, so chain verification failed on entries whose keys were reordered | High | Fixed in Phase 2 (canonical digest) |
| D19 | backend/src/controllers/doctorController.ts (searchRecords) | A category query parameter was assigned straight onto the Prisma filter, replacing the consent-derived restriction. A doctor could read a blocked category — including HIV_REPORT — simply by naming it in the query | Critical | Fixed in Phase 3 (query narrows the permitted set instead of replacing it) |
| D20 | backend/src/services/access.ts | Consent was resolved with findFirst, so with several active grants for one doctor the decision depended on row order. A block in one grant could be bypassed by a later broader grant, contradicting what the consent screen promises | High | Fixed in Phase 3 (resolveConsent combines all active grants; a block always wins) |
| D21 | backend/src/controllers/doctorController.ts (flagRecord) | Flagging performed no access check and no existence check, so a doctor could flag any record id and learn whether it existed | Moderate | Fixed in Phase 4 |
| D22 | backend/src/controllers/publicController.ts (verifyHash) | findFirst with no ordering returned an arbitrary anchor when several records share a digest, so an identical document could resolve to a stale unconfirmed anchor and be reported as unverified | Moderate | Fixed in Phase 5: prefers the most recent confirmed anchor and cross-checks it against the ledger entry |

## Appendix B — Outstanding Specification Requirements

Only unmet requirements are listed. Requirements already satisfied — the 17-table schema, audit immutability trigger, consent category enforcement, break-glass dual approval, HMS API key lifecycle and all 31 routed screens — are omitted.

| Requirement | Source | Phase |
| --- | --- | --- |
| TOTP MFA with authenticator enrolment (delivered) | Screens 2.1, 2.2 | 4 |
| Account lockout after repeated failures (delivered) | Screen 2.1 | 2 |
| File upload with AES-256-GCM envelope encryption and KMS (delivered) | §4.2 | 3, 5 |
| Client-side vault decryption (delivered) | Screen 3.2 | 3 |
| Doctor PKI and server-side signature verification (delivered) | §4.5 | 4 |
| Public prescription verification (delivered) | Screen 2.5 | 4 |
| Password change and active device sessions (delivered) | Screen 3.7 | 4 |
| Audit log hash chaining (delivered) | Module 12 | 2 |
| Audit logging on record read and download (delivered) | Module 12 | 2, 3 |
| Sub-10ms consent evaluation (partially delivered — met on the cached path, missed on a cold cache against a remote database; see §0.1) | §4.3 | 5 |
| Break-glass automatic expiry (delivered) | §4.4 | 5 |
| Emergency snapshot derived from real records (delivered) | Screen 6.2 | 5 |
| SMS and email notification delivery (delivered) | Module 11 | 5 |
| Consent expiry reminders (delivered) | Screen 3.6 | 5 |
| Tamper-evident hash anchoring (delivered) | §4.6 | 5 |
| Aadhaar OTP via UIDAI | Screen 2.2 | Deferred — §1.1 |
| PostgreSQL Row-Level Security | §3.4 | Deferred — §1.1 |
| Kafka event bus | §1 | Deferred — §1.1 |